## Worklist
Can be done later
| # | Priority | Task | Timing | Description | Estimated Hours - DA team to fill in | DA team status update | EST. Completion Date | Actual Completion Date | Test | DA Resource
|  | 1 | Reporting for EPCC 3 | 2021-01-08 | 1. Intimation via email for jobs by nature: Call and cast - after 3 weeks Any other project - after 3 months (Frequency 3 reminders) 2. Include status in daily workorder summary data or other report? Let's discuss - every Monday Trigger: Project creation date | 56 Hrs
| #REF! | 2 | Work order emails to MF partners - system temporarily changed to manual due to DI network team change. TRAT to reflect WOs approved my DIJV partner offline (from phone, without VPN) | Request Dec19 | TRAT team and Network team to resolve 1) Potential remote access to TRAT for DIJV team (Randall would need to manually enter MF approvals) best estimate at least 3mth 2) Alternative 100% tested system - e.g. check with UK for email approval applications used for PSR and TOP | Need to discuss with network team first, then I can discuss solution with you and then I can give estimates.
| 13 | 3 | On Business development jobs, the conflict check should be marked as not applicable by default. The existing option can't be used as it makes other fields NA which are required, ad a WO is required Also, EPCC 2 and 3 to include "N/A" in dropdown for conflict related fields | New | Other compliance fields remain relevant - data sharing etc., Also a WO is still required to be generated | 48 Hrs
|  | 4 | Work order linking for TSA (or Ops etc.) projects - so that same CC can be used and separate WO is an option | 2020-11-12 | We need to use the same work order raised on a TS project for the TSA part of it | 56 Hrs
|  | 5 | Add compliace check that TS Internal Risk has been obtained |  | Additional check required on raising WO 2nd question: DIJV TS Internal risk confirmation obtained? Yes/No/TBR and date | 24 Hrs
|  | 6 | Automated reminder to complete CC fields in WO after 2d |  | Email to highlight incomplete data | 32 Hrs
i |  | 7 | Employee mapping - bulk upload | 2020-05-18 |  | TBD
|  | x | Include a dashboard (TS to brainstorm on the structure) on the TRAT landing page | NA | Under consideration | Later |  | TBC
| #REF! | x | Include cost by grade and total budget (amount) as part of work order? A MF partner has commented this would be helpful - but would need to be by geography (or attach excel?) (NB Requests from MF partners) | NA | Under consideration due to complexity | Later |  | TBC
| #REF! | x | Second / additional project type identifiers required somas to record hours for different services here e.g. iDeal, TSA (possibly other SL team charging) | New | Need to consider if other SL would need | Later
Note on D3: Mantri, Shruti (IN - Mumbai): 1) difference in 2 reports 2) EPCC approvers

## Worklist old (hidden)
Can be done later
Done
# | Priority | Task | Timing | Description | Estimated Hours | DA team status update | EST. Completion Date | Actual Completion Date | Test | DA Resource
1 | 3 | Overview report available as TRAT menu - Shruti to define | Request Oct19 | Need all fields included in the daily workorder summary data report in the Overview report. We should be able to download a report with an exhaustive list of projects created during the year and their compliance status (conflict check, work order, EPCC) as at a particular date. E.g. All FY20 projects status as at 23 Mar 2020. | 3 |  |  |  |  | Pranoti, [ ]
2 | 3 | Create two email process paths for: | Request Oct19 |  | Timeline confirmation by Monday, 02/03/2020 |  |  |  |  | TBD
| 3 | Initial works order (as now) |  |  | Timeline confirmation by Monday, 02/03/2020 |  |  |  |  | TBD
| 3 | Revised works order (new path) |  | Save button to be clicked | Timeline confirmation by Monday, 02/03/2020 |  |  |  |  | TBD
3 | 3 | TS to provide revised wording for each email |  | TS will be providing with revised text | Timeline confirmation by Monday, 02/03/2020 |  |  |  |  | TBD
4 | 2 | Amend WO to add text as a footnote - "EPCC stage 1"
5 | 6 | Inclusion of EPCC sign off (process originally initiated mid-2019) - WO is EPCC stage 1 - DI CC sign off is EPCC stage 2 - WO closure, addition of filing dates and approval by IJV partner EPCC stage 3 | Mid-2019 | TRAT team was to investigate potential for separate systems for approvals vs time reporting 1) Cost 2) Timeline 3) Logistics |  |  | [06 Jan 2020]
6 | x | Include cost by grade and total budget (amount) as part of work order? A MF partner has commented this would be helpful - but would need to be by geography (or attach excel?) (NB Requests from MF partners) | NA | Under consideration due to complexity | Later |  | TBC
7 | n/a | Remove projects for CS team from daily reports | 2019-10-01 | Remove Maninder, Abhimanyu, Pravesh |  | Done |  | 2020-03-10
8 | 2 | Add new fields to Work order (pre-requirment for EPCC) - TS sent an updated template | 2019-10-01 | Please refer to Tab 2 - #8 for the fields to be added, they are highlighted in red |  |  | 2019-12-19
9 | 4 | Work order emails to MF partners - system temporarily changed to manual due to DI network team change | Request Dec19 | TRAT team and Network team to resolve 1) Potential remote access to TRAT for DIJV team (Randall would need to manually enter MF approvals) best estimate at least 3mth 2) Alternative 100% tested system - e.g. check with UK for email approval applications used for PSR and TOP
10 | n/a | Update DI dccs conflict check details in the work order (IJV approval via EPCC stage) without re-issuing WO to MF Avoids duplicate WO issued for approval by MF | Request Dec19 | Not scheduled |  | Done |  | 2020-02-20
11 | n/a | Where MF WO approval or CC not received we need IJV partner approval for closure with reason code | New |  |  | Done | 28/02/2020 | 2020-03-01
12 | x | Second / additional project type identifiers required somas to record hours for different services here e.g. iDeal, TSA (possibly other SL team charging) | New | Need to consider if other SL would need | Later
13 | x | On Business development jobs, the conflict check should be marked as not applicable by default | New | As Discussed It will be managed manually | Later
14 | 1 | Recepient email addresses on Sean's work order approvals need to be corrected. Emails need to be sent to only Indian email ids. | Request Dec19 | Done as per Riddhi's input, however, need to check. Sean is getting the following error while approving - "The email address is not valid". Also, the recipient's .com email address is getting copied twice. Please see the screenshot on Tab 1 - #14. Also, we need to add the process lead on the email too. |  |  | 17/3/2020 | 2020-03-17
15 | n/a | Project creation page - conflict check number | 2020-03-20 |  |  | Done | 2020-11-03 | 2020-02-20
16 | n/a | Resource Allocation Issue has been solved permanantly. | Non-TS | Non-TS | Non-TS | Done | Non-TS | Non-TS
17 | n/a | Correct affected data of resource allocation | Non-TS | Non-TS | Non-TS | Done | Non-TS | Non-TS
18 | n/a | Field Added in project creation it should be visible to TS team only | 2020-03-20 |  |  | Done | 16/3/2020 | 2020-03-10
19 | n/a | In project creation remove email validation , as its acception only deloitte email id. | 2020-03-20 |  |  | Done | 18/3/2020 | 2020-03-17
Note on C14: Mantri, Shruti (IN - Mumbai): change to 2
Note on B15: Mantri, Shruti (IN - Mumbai): highlight with Hari